## Decision Point Tracker
PJM Cycle 1 Decision Point Tracker — Zonevex
Track readiness deposits, milestone deadlines, and withdrawal penalties across Decision Points I, II, and III
Decision Point | Req # | Category | Requirement | What You Must Provide | How to Prepare | Status | Target Date | Evidence Document | OATT/Manual Ref | Consequence of Failure
APPLICATION (Apr 27 2026) | A1 | Site Control | 100% site control of generating facility | Deed, lease, option, or development agreement covering full project footprint | Assemble all land agreements; verify coverage includes access roads + laydown + setbacks | Not Met | April 20 2026 |  | OATT §302 | Deficiency notice → 10 business day cure → termination
APPLICATION (Apr 27 2026) | A2 | Site Control | Documents in applicant entity name | Every site control document must show EXACT entity name matching application | Complete entity name verification matrix (Template C); fix mismatches before submission | Not Met | April 20 2026 |  | OATT §302 | Deficiency → most common rejection cause
APPLICATION (Apr 27 2026) | A3 | Site Control | Term >= 1 year from deadline | All site control documents must expire AFTER April 27 2027 | Check every expiration date; execute amendments if any expire before April 27, 2027 | Not Met | April 20 2026 |  | FERC Order 2023 | Deficiency → moderate cure difficulty (requires landowner cooperation)
APPLICATION (Apr 27 2026) | A4 | Site Control | Solar: land adequacy engineering analysis | Panel type, GCR, row spacing, acreage calculation demonstrating MW capacity | Engage engineer; calculate (panel count x wattage = MW); compare required vs controlled acreage | Not Met | April 15 2026 |  | Manual 14H | Deficiency → may require MW reduction
APPLICATION (Apr 27 2026) | A5 | Financial | Study deposit funded | $75K-$400K based on capacity tier, in cash/ILOC/surety bond | Verify amount via PJM calculator; arrange funding instrument; allow 1-2 weeks for ILOC | Not Met | April 15 2026 |  | Manual 14H §6 | Deficiency → fund correct amount within 10 days
APPLICATION (Apr 27 2026) | A6 | Financial | Readiness Deposit No. 1 funded | $4,000 x MW in cash/ILOC/surety bond | Calculate: $4000 x [MW]; arrange funding instrument | Not Met | April 15 2026 |  | Manual 14H §6 | Deficiency → fund correct amount within 10 days
APPLICATION (Apr 27 2026) | A7 | Financial | Application fee | 5 | 000 | Include with submission payment | Not Met | April 27 2026 |  | Manual 14H | Deficiency
APPLICATION (Apr 27 2026) | A8 | Technical | Site plan (Attachment N) complete | Equipment layout, property boundaries, POI, gen-tie route, access, setbacks, scale/north arrow | Engage surveyor/engineer; ensure MW matches application; every element shown on plan must be within controlled land | Not Met | April 15 2026 |  | Manual 14G Att N | Deficiency → requires engineering revision
APPLICATION (Apr 27 2026) | A9 | Technical | System Impact Study Data Forms (B-1/B-2) | All technical parameters + PSSE dynamic model (.dyr, v33+) | Complete B-1 from equipment datasheets; request PSSE models from manufacturer (4-8 week lead time) | Not Met | April 1 2026 |  | Manual 14G Att B-1/B-2 | Deficiency → high cure difficulty (manufacturer lead times)
APPLICATION (Apr 27 2026) | A10 | Technical | POI specifically identified | Exact PJM facility name + voltage level (e.g., 'XYZ Substation 138 kV bus') | Verify name via PJM queue spreadsheet and Queue Scope; contact InterconnectionSupport@pjm.com to pre-validate | Not Met | April 15 2026 |  | Manual 14G | Deficiency → low cure difficulty (resubmit corrected POI)
APPLICATION (Apr 27 2026) | A11 | Technical | One-line diagram complete | Electrical one-line from generator terminals through step-up transformer to POI | Engage electrical engineer; must match equipment specs and site plan | Not Met | April 15 2026 |  | Manual 14G | Deficiency → moderate cure difficulty
APPLICATION (Apr 27 2026) | A12 | Technical | MW consistency across all documents | Nameplate MW identical on: application, site plan, engineering analysis, B-1 form | Create MW cross-reference table; check every document | Not Met | April 20 2026 |  | Manual 14H | Deficiency → low cure difficulty (correct inconsistent document)
APPLICATION (Apr 27 2026) | A13 | Agreements | ASA fully executed | Current Cycle 1 version signed by authorized representative | Download current ASA from PJM portal; have legal review; execute before submission | Not Met | April 20 2026 |  | OATT Part VII | Deficiency → execute correct version
APPLICATION (Apr 27 2026) | A14 | Agreements | Officer Certification signed | Current PJM Cycle 1 form signed by person with corporate authority | Download current form; verify signatory has authorization document | Not Met | April 25 2026 |  | Manual 14H | Deficiency → sign correct form
APPLICATION (Apr 27 2026) | A15 | Permitting | Permitting pathway documented | Permit matrix: name, authority, status, timeline for all federal/state/local permits | Research state requirements (see Playbook Section 10); document even if no applications filed yet | Not Met | April 20 2026 |  | Manual 14H | Not formally deficient but signals unreadiness to PJM
APPLICATION (Apr 27 2026) | A16 | Platform | NextGen account active with Read/Write access | Verified login, Company Profile complete, Read/Write role confirmed | Log in now; non-members contact Account Manager for CAM assignment (allow business days) | Not Met | March 15 2026 |  | NextGen User Guide | Cannot submit without active account
APPLICATION (Apr 27 2026) | A17 | QA | Pre-submission QA signoff complete | Template D signed by preparer + reviewer + approver | Complete all 15 verification checks; do not submit until all pass | Not Met | April 22 2026 |  | N/A | Risk of preventable deficiency
DECISION POINT 1 (~Oct 2026) | D1 | Site Control | 100% generating facility — extended term | Site control extended for additional 1-year term beyond initial evidence | If initial documents expire within next year: execute term amendments with landowners | Not Met | Within 30 days of Phase I report |  | OATT §302 / §309 | Project terminated; deposits forfeited
DECISION POINT 1 (~Oct 2026) | D2 | Site Control | 50% interconnection facility site control | Easements or options covering 50% of gen-tie route from facility to POI, 1-year term | Map probable routes during Phase I; secure options on parcels along 2-3 routes; path may change | Not Met | Within 30 days of Phase I report |  | OATT §302 | Project terminated; deposits forfeited
DECISION POINT 1 (~Oct 2026) | D3 | Financial | Readiness Deposit No. 2 funded | 10% of Phase I network upgrade cost allocation minus RD1, in cash/ILOC/surety bond | Cannot calculate until Phase I results received; have capital reserves or committed financing ready for 30-day funding window | Not Met | Within 30 days of Phase I report |  | Manual 14H §6.2 | Project terminated; deposits forfeited
DECISION POINT 1 (~Oct 2026) | D4 | Decision | Proceed to Phase II or withdraw | 30-day decision window after receiving Phase I study report | Review upgrade costs against economic model (see Playbook Section 9); calculate implied project return; assess penalty exemption eligibility if considering withdrawal | Not Decided | Within 30 days of Phase I report |  | §309 | Must decide within 30 days or project is terminated
DECISION POINT 2 (~May 2027) | D5 | Site Control | Continued generating facility site control | Updated evidence if prior documents are expiring | Monitor all site control expiration dates; execute extensions proactively | Not Met | Within 30 days of Phase II report |  | OATT §302 | Project terminated
DECISION POINT 2 (~May 2027) | D6 | Financial | Readiness Deposit No. 3 funded | 20% of Phase II network upgrade cost allocation minus total RDs (RD1+RD2) | Cannot calculate until Phase II results; prepare capital for worst-case scenario based on Phase I costs | Not Met | Within 30 days of Phase II report |  | Manual 14H §6.2 | Project terminated; deposits forfeited
DECISION POINT 2 (~May 2027) | D7 | Documentation | Updated readiness documentation | Current status report: permitting, financing, site control, project development progress | Prepare status report with: permit update, financing status, site control summary, construction readiness assessment | Not Met | Within 30 days of Phase II report |  | Manual 14H | Project terminated
DECISION POINT 2 (~May 2027) | D8 | Decision | Proceed to Phase III or withdraw | 30-day decision window after receiving Phase II study report | Review refined costs; compare to Phase I (check >25% increase for penalty exemption); assess whether accelerated track applies (<$5M upgrades) | Not Decided | Within 30 days of Phase II report |  | OATT Part VII | Must decide within 30 days
DECISION POINT 3 (~Dec 2027) | D9 | Site Control | 100% generating facility — all forms | Full ownership, lease, or exercised option (NOT unexercised option) | If using options: plan to exercise before DP3. Budget for exercise costs. | Not Met | Within 30 days of Phase III report |  | OATT §302 | Withdrawal required; 9x penalty unless exempt
DECISION POINT 3 (~Dec 2027) | D10 | Site Control | 100% interconnection facilities — 3-year term | Complete gen-tie route, substation land, all easements — control extending through ~December 2030 | Secure remaining 50% of interconnection facility path; negotiate 3-year terms. WARNING: TO may change path during Phase III — budget $50-200K for emergency acquisition. | Not Met | Within 30 days of Phase III report |  | OATT §302 | Withdrawal required; 9x penalty unless exempt. This is the #1 DP3 killer.
DECISION POINT 3 (~Dec 2027) | D11 | Agreement | Enter GIA negotiation | ~35 business day negotiation window for Generation Interconnection Agreement | Engage legal counsel experienced with PJM GIAs; review standard GIA terms in advance; prepare negotiation positions on key provisions | Not Started | ~35 business days from DP3 |  | OATT §314 | Must execute or withdraw
DECISION POINT 3 (~Dec 2027) | D12 | Decision | Execute GIA or withdraw | Final commitment — withdrawal at DP3 subject to 9x study deposit penalty unless exemption applies | Calculate total forward cost vs. expected project NPV; check penalty exemptions; if withdrawing, document exemption basis using Template E | Not Decided | End of GIA negotiation window |  | OATT Part VII | 9x penalty (e.g., $250K deposit = $2.25M penalty) unless exempt
POST-DP3 (~Feb 2028) | D13 | Agreement | GIA executed | Signed Generation Interconnection Agreement | Final legal review; execute; transition to construction planning | Not Started | Per GIA timeline |  | Manual 14G
POST-DP3 (~Feb 2028) | D14 | Financial | Construction deposits per GIA | Financial commitments per executed GIA terms | Budget per GIA requirements | Not Started | Per GIA terms |  | Per GIA